## sheetjs
Project Name | PC | Architecture | Interior | Landscape | PS | AH | TCH | BH | DYT | PP | BUA | CD1 Start date | CD1 Planned End date | CD1 Ext end date | CD1 Deliverables | CD1 Allocated | CD1 Consumed | CD1 Status Progress | CD2 Start date | CD2 End date | CD2 Ext end date | CD2 Deliverables | CD2 Allocated | CD2 Consumed | CD2 Status Progress | CD3 Start date | CD3 End date | CD3 Ext end date | CD3 Deliverables | CD3 Allocated | CD3 Consumed | CD3 Status Progress | CD4 Start date | CD4 End date | CD4 Ext end date | CD4 Deliverables | CD4 Allocated | CD4 Consumed | CD4 Status Progress | CD5 Start date | CD5 End date | CD5 Ext end date | CD5 Deliverables | CD5 Allocated | CD5 Consumed | CD5 Status Progress | SD1 Start date | SD1 End date | SD1 Ext end date | SD1 Deliverables | SD1 Allocated | SD1 Consumed | SD1 Status Progress | SD2 Start date | SD2 End date | SD2 Ext end date | SD2 Deliverables | SD2 Allocated | SD2 Consumed | SD2 Status Progress | SD3 Start date | SD3 End date | SD3 Ext end date | SD3 Deliverables | SD3 Allocated | SD3 Consumed | SD3 Status Progress | SD4 Start date | SD4 End date | SD4 Ext end date | SD4 Deliverables | SD4 Allocated | SD4 Consumed | SD4 Status Progress | MC Start date | MC End date | MC Ext end date | MC Deliverables | MC Allocated | MC Consumed | MC Status Progress | AD Start date | AD End date | AD Ext end date | AD Deliverables | AD Allocated | AD Consumed | AD Status Progress | DD1 Start date | DD1 End date | DD1 Ext end date | DD1 Deliverables | DD1 Allocated | DD1 Consumed | DD1 Status Progress | DD2 Start date | DD2 End date | DD2 Ext end date | DD2 Deliverables | DD2 Allocated | DD2 Consumed | DD2 Status Progress | DD3 Start date | DD3 End date | DD3 Ext end date | DD3 Deliverables | DD3 Allocated | DD3 Consumed | DD3 Status Progress | DD4 Start date | DD4 End date | DD4 Ext end date | DD4 Deliverables | DD4 Allocated | DD4 Consumed | DD4 Status Progress | TD1 Start date | TD1 End date | TD1 Ext end date | TD1 Deliverables | TD1 Allocated | TD1 Consumed | TD1 Status Progress | TD2 Start date | TD2 End date | TD2 Ext end date | TD2 Deliverables | TD2 Allocated | TD2 Consumed | TD2 Status Progress | TD3 Start date | TD3 End date | TD3 Ext end date | TD3 Deliverables | TD3 Allocated | TD3 Consumed | TD3 Status Progress | TD4 Start date | TD4 End date | TD4 Ext end date | TD4 Deliverables | TD4 Allocated | TD4 Consumed | TD4 Status Progress | TD5 Start date | TD5 End date | TD5 Ext end date | TD5 Deliverables | TD5 Allocated | TD5 Consumed | TD5 Status Progress | WD20 Start date | WD20 End date | WD20 Ext end date | WD20 Deliverables | WD20 Allocated | WD20 Consumed | WD20 Status Progress | WD40 Start date | WD40 End date | WD40 Ext end date | WD40 Deliverables | WD40 Allocated | WD40 Consumed | WD40 Status Progress | WD60 Start date | WD60 End date | WD60 Ext end date | WD60 Deliverables | WD60 Allocated | WD60 Consumed | WD60 Status Progress | WD80 Start date | WD80 End date | WD80 Ext end date | WD80 Deliverables | WD80 Allocated | WD80 Consumed | WD80 Status Progress | WD100 Start date | WD100 End date | WD100 Ext end date | WD100 Deliverables | WD100 Allocated | WD100 Consumed | WD100 Status Progress | DC Start date | DC End date | DC Ext end date | DC Deliverables | DC Allocated | DC Consumed | DC Status Progress | CO Start date | CO End date | CO Ext end date | CO Deliverables | CO Allocated | CO Consumed | CO Status Progress
H&S Page Three Residences, Noida | 20009 | Palin Sikari | Surabhi Garg | Not in scope | Active | 6300 | 6706 | -406 | Palin (2.5%), Rohit(2.5%) | 85% | 126000 | 2021-03-01 | 2021-05-11 | No data | No data | 189 | 104 | 100% | No Data | No Data | No Data | No Data | 227 | 0 | 0% | 2021-12-09 | 2024-10-18 | No data | No data | 189 | 700 | 100% | No Data | No Data | No Data | No Data | 151 | 0 | No Data | No Data | No Data | No Data | No Data | No Data | No Data | No Data | 2021-04-02 | 2022-11-11 | No data | No data | 378 | 65 | 100% | 2022-07-04 | 2022-07-22 | No data | No data | 271 | 20 | 100% | 2022-01-03 | 2024-08-27 | No data | No data | 214 | 193 | 100% | 2024-08-21 | 2024-08-31 | No data | No data | 214 | 59 | 100% | 2021-12-15 | 2024-10-04 | No data | No data | 314 | 54 | 100% | 2021-03-01 | 2021-11-30 | No data | No data | 315 | 312 | 100% | 2021-05-05 | 2024-02-12 | No data | No data | 378 | 787 | 100% | 2021-12-08 | 2024-08-02 | No data | No data | 271 | 546 | 100% | 2022-01-19 | 2023-12-01 | No data | No data | 214 | 235 | 100% | 2022-03-14 | 2024-07-03 | No data | No data | 214 | 56 | 100% | 2021-04-13 | 2024-06-14 | No data | No data | 132 | 52 | 100% | No data | No data | No data | No data | 44 | 0 | 100% | 2021-05-27 | 2024-03-01 | No data | No data | 88 | 75 | 100% | 2024-02-26 | 2024-03-05 | No data | No data | 88 | 12 | 100% | No data | No data | No data | No data | 88 | 0 | 100% | 2021-05-07 | 2023-01-30 | No data | No data | 139 | 456 | 100% | 2022-03-11 | 2024-01-02 | No data | No data | 277 | 396 | 100% | 2022-03-10 | 2025-02-03 | No data | No data | 416 | 941 | 100% | 2022-11-03 | 2025-05-08 | No data | No data | 271 | 231 | 100% | 2024-09-19 | 2025-06-25 | No data | No data | 271 | 700 | 100% | 2022-03-07 | 2025-10-17 | No data | No data | 630 | 694 | 0% | No Data | No Data | No Data | No Data | 315 | 25 | 0%
NBCC FCIL - Office Building, NOIDA | 21029 | Palin Sikari | Not in scope | Pallavi Bharadwaj | Active | 0 | 7240 | -7240 | Palin (5%), Shivani(10%), Rohit(5%) | 70% | 121160 | 2021-05-17 | 2021-07-20 | No data | No data | 0 | 447 | 100% | 2021-10-12 | 2022-02-10 | No data | No data | 0 | 20 | 100% | 2025-01-14 | 2025-01-21 | No data | No data | 0 | 4 | 100% | No Data | No Data | No Data | No Data | No Data | No Data | No Data | No Data | No Data | No Data | No Data | No Data | No Data | No Data | 2021-05-26 | 2024-10-10 | No Data | No Data | 0 | 285 | 100% | 2021-09-04 | 2021-09-16 | No data | No data | 0 | 100 | 100% | 2022-04-05 | 2025-07-18 | No data | No data | 0 | 395 | 100% | No data | No data | No data | No data | No data | No data | 0% | No data | No data | No data | No data | No data | No data | 0% | 2021-06-29 | 2022-09-21 | No data | No data | 0 | 585 | 100% | 2021-07-05 | 2023-06-23 | No data | No data | 0 | 905 | 100% | 2022-01-04 | 2023-05-25 | No data | No data | 0 | 237 | 100% | 2022-11-11 | 2022-12-02 | No data | No data | 0 | 111 | 100% | No Data | No Data | No Data | No Data | No Data | No Data | 0% | 2021-06-30 | 2022-09-23 | No data | No data | 0 | 345 | 100% | No data | No data | No data | No data | 0 | 2 | 0% | No data | No data | No data | No data | 0 | 0 | 0% | 2023-04-13 | 2023-04-18 | No data | No data | 0 | 13 | 100% | No data | No data | No data | No data | No data | No data | 0% | 2021-11-15 | 2023-09-27 | No data | No data | 0 | 316 | 100% | 2022-05-10 | 2024-06-21 | No data | No data | 0 | 342 | 100% | 2022-05-25 | 2025-07-31 | No data | No data | 0 | 1082 | 100% | No Data | No Data | No Data | No Data | No Data | No Data | 0% | 2024-05-13 | 2025-08-29 | 2025-02-13 | No Data | 0 | 1159 | 0% | No data | No data | No data | No data | 0 | 399 | 0% | No data | No data | No data | No data | 0 | 38 | 0%
M3M The Cullinan - MLU, NOIDA Sec-94 | 22049.1 | Palin Sikari | Himanshu Verma, Ashulika Arora, Surabhi Garg | Pallavi Bharadwaj | Active | 48000 | 61779 | -13779 | Sebanti(30%), Palin(40%) Alok(85%), Sonam(75%), Abhishek(100%), Vishal(100%), Avdaman (75%), Anjali(100%), Yash(100%),Rahul(50%) | 25% | 50000000 | 2022-10-31 | 2024-11-08 | No data | No data | 1680 | 922 | 0% | 2022-11-28 | 2025-08-21 | No data | No data | 1728 | 780 | 0% | 2023-01-14 | 2025-10-28 | No data | No data | 1152 | 861 | 100% | 2023-02-27 | 2024-01-24 | No data | No data | 1152 | 951 | 0% | No data | No data | No data | No data | No data | No data | No data | 2025-05-06 | 2025-09-11 | 2026-01-30 | No data | 2880 | 4037 | 80.77% | 2025-06-25 | 2025-08-11 | 2025-09-11 | No data | 2064 | 3884 | 100% | 2022-12-19 | 2025-11-04 | No data | No data | 1632 | 2630 | 100% | 2023-08-21 | 2023-12-18 | No data | No data | 1632 | 63 | 0% | 2025-05-06 | 2025-12-06 | No data | No data | 2400 | 241 | 0% | 2025-05-06 | 2025-10-07 | No data | No data | 960 | 890 | 0% | 2025-03-07 | 2025-10-31 | 2026-03-13 | No data | 1680 | 4377 | 31.88% | 2025-08-21 | 2025-10-31 | No data | No data | 1200 | 2871 | 100% | 2023-04-19 | 2025-10-27 | No data | No data | 960 | 586 | 100% | 2023-11-06 | 2025-09-27 | No data | No data | 960 | 52 | 0% | 2023-03-03 | 2025-08-29 | No data | No data | 1008 | 154 | 0% | 2023-03-03 | 2025-08-29 | No data | No data | 336 | 8 | 0% | 2025-03-27 | 2025-10-16 | No data | No data | 672 | 248 | 0% | 2025-08-15 | 2025-09-30 | 2026-03-13 | 5 | 672 | 2352 | 100% | 2025-09-01 | 2025-09-30 | No data | No data | 672 | 0 | 0% | 2023-04-03 | 2025-09-29 | No data | 8 | 1056 | 2035 | 100% | 2023-06-01 | 2025-08-14 | 2025-11-07 | 34 | 2112 | 7748 | 100% | 2025-07-17 | 2025-11-15 | 2026-04-17 | 2000-10-02 | 3168 | 17137 | 18.48% | 2023-08-03 | 2025-11-07 | No data | No data | 2112 | 4857 | 0% | 2025-09-01 | 2025-12-31 | No data | No data | 2112 | 5810 | 0% | 2025-11-01 | 2027-11-30 | No data | No data | 9600 | 2182 | 0% | 2027-11-01 | 2027-11-30 | No data | No data | 2400 | 0 | 0%
Atulit (Tulip Mall), Ranchi | 23066 | Palin Sikari | Surabhi Garg | Not in scope | Active | 4100 | 5434 | -1334 | No Arch Deply |  | 107600 | 2024-02-19 | 2024-02-21 | No data | No data | 148 | 24 | No data | 2025-01-14 | 2025-01-21 | No data | No data | 197 | 11 | No data | 2024-01-08 | 2024-05-15 | No data | No data | 148 | 329 | No data | No data | No data | No data | No data | No data | No data | No data | No data | No data | No data | No data | No data | No data | No data | 2023-10-21 | 2024-10-17 | No data | No data | 279 | 129 | No data | No data | No data | No data | No data | 246 | 1 | No data | 2023-09-18 | 2024-08-31 | No data | No data | 172 | 295 | No data | No data | No data | No data | No data | 0 | 0 | No data | No data | No data | No data | No data | 205 | 0 | No data | No data | No data | No data | No data | 205 | 0 | No data | 2024-02-05 | 2024-02-09 | No data | No data | 131 | 517 | No data | 2023-05-09 | 2024-07-11 | No data | No data | 115 | 893 | No data | 2023-05-29 | 2025-04-21 | No data | No data | 82 | 444 | No data | No data | No data | No data | No data | 0 | 0 | No data | No data | No data | No data | No data | 111 | 0 | No data | No data | No data | No data | No data | 37 | 0 | No data | 2024-05-23 | 2024-06-10 | No data | No data | 49 | 52 | No data | No data | No data | No data | No data | 49 | 0 | No data | No data | No data | No data | No data | 0 | 0 | No data | No data | No data | No data | No data | 135 | 0 | No data | 2023-02-06 | 2024-02-01 | No data | No data | 226 | 17 | No data | 2023-02-02 | 2024-10-23 | No data | No data | 316 | 333 | No data | No data | No data | No data | No data | 0 | 0 | No data | 2023-09-12 | 2025-08-20 | No data | No data | 226 | 1277 | No data | 2023-05-03 | 2025-10-30 | No data | No data | 820 | 287 | 0% | No data | No data | No data | No data | 205 | 1 | 0%
Trevana (Karyan) -GH, Ghaziabad | 23087 | Palin Sikari | Not in scope | Not in scope | Active | 12800 | 8069 | 4731 | Palin (15%), Simple(100%), Avdaman(25%), Alok(15%), Shivani(90%), Sonam (25%), Dishant(50%) | 27% | 2286588 | 2024-03-04 | 2025-11-07 | No data | 1 | 461 | 2095 | 100% | 2025-07-15 | 2025-08-01 | No data | 1 | 614 | 242 | 100% | 2024-10-22 | 2025-09-19 | 2026-01-15 | 1 | 0 | 0 | 0% | No Data | No Data | No Data | No Data | No Data | No Data | No Data | No Data | No Data | No Data | No Data | No Data | No Data | No Data | 2024-06-19 | 2025-05-16 | 2026-01-22 | 80 | 858 | 3092 | 98.75 | 2024-08-20 | 2025-05-16 | No data | 13 | 768 | 3209 | 100% | 2024-06-19 | 2025-09-15 | No data | 48 | 550 | 668 | 100% | No data | No data | No data | No data | No data | No data | No data | 2025-08-12 | 2025-09-30 | 2026-01-30 | No data | 640 | 61 | 100% | 2024-08-11 | 2025-09-30 | No data | 1 | 640 | 3656 | 100% | 2025-09-01 | 2025-10-31 | 2026-02-16 | 137 | 410 | 1180 | 36% | 2025-09-16 | 2025-10-31 | 2026-01-30 | 24 | 358 | 348 | 0% | 2025-09-30 | 2025-12-24 | 2026-03-30 | 63 | 256 | 16 | 22.22% | No data | No data | No data | No data | No data | No data | No data | 2025-09-29 | 2025-11-20 | 2026-03-31 | 148 | 346 | 0 | 0% | 2025-10-10 | 2025-11-20 | 2026-03-31 | No data | 115 | 0 | 0% | 2025-10-10 | 2025-11-20 | 2026-03-31 | 16 | 154 | 0 | 0% | 2025-10-10 | 2025-11-30 | 2026-03-31 | 65 | 154 | 0 | 0% | No data | No data | No data | No data | No data | No data | 0% | 2025-10-10 | 2025-10-31 | 2026-01-30 | 8 | 422 | 93 | 0% | 2025-10-27 | 2025-12-23 | 2026-02-28 | 59 | 704 | 0 | 0% | 2025-11-21 | 2026-02-25 | 2026-04-30 | 154 | 986 | 0 | 0% | No data | No data | No data | No data | No data | No data | No data | 2025-12-30 | 2026-03-31 | 2026-05-15 | 113 | 704 | 2 | 0% | 2025-10-01 | 2027-01-31 | No data | No data | 2560 | 0 | 0% | 2027-01-01 | 2027-01-31 | No data | No data | 640 | 0 | 0%
Golf Estate(Jashn Realty) - Plotted Development, Lucknow | 25132 | Palin Sikari | Himanshu Verma | Not in scope | Active | 16400 | 5493 | 10907 | Palin(20%), Himanshu(20%), Suyesh(5%), Sebanti(60%), Agrima(50%), Rohit(62.5%), Akhil(100%), Anshuman(50%), Dishant(50%), Rahul(50%0 | 19% | 1861552 | 2025-07-07 | 2025-08-22 | No data | 2 | 590 | 1139 | 50% | 2025-07-07 | 2025-08-22 | No data | 2 | 787 | 501 | 50% | 2025-08-25 | 2025-10-01 | 2025-10-01 | 2 | 492 | 1165 | 50% | No Data | No Data | No Data | No Data | No Data | No Data | No Data | 2025-08-14 | 2025-08-31 | No data | No data | 98 | 0 | 0% | 2025-08-18 | 2025-09-19 | 2025-10-03 | 159 | 1099 | 561 | 8.81% | 2025-09-15 | 2025-10-03 | 2025-12-01 | 15 | 984 | 790 | 6.67% | 2025-09-02 | 2025-10-30 | No data | 6 | 705 | 99 | 100% | No data | No data | No data | No data | No data | No data | No data | 2025-08-04 | 2025-10-30 | No data | 1 | 820 | 152 | 100% | 2025-09-08 | 2025-10-27 | 2025-10-09 | 2 | 820 | 105 | 50% | 2025-10-06 | 2025-11-14 | No data | 175 | 525 | 666 | 3.43% | 2025-09-08 | 2025-11-14 | No data | 15 | 459 | 151 | 6.67% | 2025-08-25 | 2025-11-14 | 2025-12-19 | 201 | 328 | 345 | 100% | No data | No data | No data | No data | No data | No data | No data | 2025-10-24 | 2025-11-21 | No data | 176 | 443 | 78 | 0% | 2025-10-31 | 2025-11-21 | No data | No data | 148 | 0 | 0% | 2025-11-07 | 2025-11-21 | No data | 16 | 197 | 10 | 0% | 2025-11-10 | 2025-11-17 | 2025-12-24 | 206 | 197 | 125 | 0% | No data | No data | No data | No data | No data | No data | 0% | 2025-09-29 | 2025-11-28 | No data | 20 | 541 | 111 | 0% | 2025-10-13 | 2025-12-26 | No data | 76 | 902 | 331 | 10.53 | 2025-10-20 | 2026-02-09 | No data | 258 | 1263 | 459 | 0% | No data | No data | No data | No data | No data | No data | No data | 2025-11-11 | 2025-11-30 | 2026-02-09 | 226 | 902 | 268 | 0% | 2025-09-29 | 2029-12-31 | No data | No data | 3280 | 0 | 0% | 2030-03-01 | 2030-03-31 | No data | No data | 820 | 0 | 0%
Golf Estate(Jashn Realty) - Club, Lucknow | 25133 | Palin Sikari | Himanshu Verma | Not in scope | Active | 6000 | 1642 | 4358 | Palin(17.5), Himanshu(10%), Vrinda(25), Cheeranjeev(90%), Rohit(30%), Anshuman(50%) | 18% | 63563 | 2025-05-21 | 2025-08-07 | No data | 1 | 210 | 3 | 100% | 2025-05-21 | 2025-08-07 | No data | 1 | 288 | 0 | 100% | 2025-09-01 | 2025-10-15 | 2026-01-30 | No data | 216 | 192 | 0% | No data | No data | No data | No data | No data | No data | No data | No data | No data | No data | No data | No data | No data | No data | 2025-09-29 | 2025-10-03 | 2025-10-17 | 30 | 408 | 23 | 0% | 2025-09-29 | 2025-10-17 | No data | No data | 360 | 8 | 0% | 2025-10-16 | 2025-10-20 | 2026-01-09 | 22 | 258 | 240 | 0% | No data | No data | No data | No data | No data | No data | No data | 2025-10-06 | 2025-10-31 | 2025-11-14 | 1 | 300 | 7 | 0% | 2025-10-08 | 2025-10-26 | No data | 1 | 300 | 5 | 100% | 2025-10-29 | 2025-11-22 | 2026-01-16 | 52 | 192 | 169 | 0% | 2025-10-29 | 2025-11-22 | 2026-01-16 | No data | 168 | 18 | 0% | 2025-10-27 | 2025-11-21 | 2026-02-27 | 52 | 120 | 28 | 0% | No data | No data | No data | No data | No data | No data | No data | 2025-11-20 | 2025-12-07 | No data | 29 | 162 | 0 | 0% | 2025-11-20 | 2025-12-07 | No data | 0 | 54 | 0 | 0% | 2025-11-20 | 2025-12-07 | No data | 27 | 72 | 0 | 0% | 2025-11-20 | 2025-12-07 | 2026-03-06 | 58 | 72 | 0 | 0% | No data | No data | No data | No data | No data | No data | 0% | 2025-11-13 | 2025-11-20 | No data | 2 | 198 | 3 | 0% | 2025-11-24 | 2025-12-26 | No data | 15 | 330 | 8 | 0% | 2025-11-27 | 2025-12-28 | 2026-02-09 | 57 | 462 | 10 | 0% | No data | No data | No data | No data | No data | No data | No data | 2025-12-01 | 2025-12-26 | 2026-05-01 | 58 | 330 | 2 | 0% | 2025-11-01 | 2026-12-31 | No data | No data | 1200 | 0 | 0% | 2026-12-01 | 2026-12-31 | No data | No data | 300 | 0 | 0%
MKS Parking | 18002 | Balraj Singh | Not in scope | Not in scope | Active | 500 | 809 | 309 | Bipin (2%) | 74.8% | 214204 | No data | No data | No data | No data | 25 | 25 | 100% | No data | No data | No data | No data | 30 | 25 | 100% | No data | No data | No data | No data | 0 | 0 | 100% | No data | No data | No data | No data | 0 | 0 | 100% | No data | No data | No data | No data | 0 | 0 | 100% | No data | No data | No data | No data | 48 | 217 | 100% | No data | No data | No data | No data | 32 | 0 | 100% | No data | No data | No data | No data | 0 | 0 | 100% | No data | No data | No data | No data | 0 | 0 | 100% | No data | No data | No data | No data | 25 | 0 | 100% | 2025-02-04 | 2025-02-12 | No data | No data | 25 | 27 | 100% | No data | No data | No data | No data | 48 | 46 | 100% | No data | No data | No data | No data | 32 | 47 | 100% | No data | No data | No data | No data | 0 | 0 | 100% | No data | No data | No data | No data | 0 | 0 | 100% | No data | No data | No data | No data | 18 | 1 | 100% | No data | No data | No data | No data | 3 | 0 | 100% | 2022-01-10 | 2022-01-31 | No data | No data | 9 | 10 | 100% | No data | No data | No data | No data | 0 | 0 | 100% | No data | No data | No data | No data | 0 | 0 | 100% | No data | No data | No data | No data | 16 | 124 | 100% | No data | No data | No data | No data | 37 | 126 | 100% | 2024-09-10 | 2025-09-12 | No data | No data | 54 | 124 | 100% | No data | No data | No data | No data | 0 | 0 | 100% | No data | No data | No data | No data | 0 | 0 | 100% | 2021-03-16 | 2026-12-31 | No data | No data | 75 | 37 | 0% | 2025-01-12 | 2026-01-12 | No data | No data | 25 | 0 | 0%
Ace Plot-G | 18007 | Balraj Singh | Not in scope | Not in scope | Active | 0 | 5370 | -5370 | Bipin(40%), Shankey(40%), Anil (100%), Avdesh(100%) | 5% | 2378500 | 2021-06-09 | 2021-12-06 | No data | No data | 0 | 444 | 100% | 2021-02-22 | 2024-04-23 | No data | No data | 0 | 122 | 100% | No data | No data | No data | No data | 0 | 0 | 100% | No data | No data | No data | No data | 0 | 0 | 100% | No data | No data | No data | No data | 0 | 0 | 100% | 2021-03-08 | 2024-05-01 | No data | No data | 0 | 929 | 100% | 2023-03-03 | 2023-06-30 | No data | No data | 0 | 433 | 100% | No data | No data | No data | No data | 0 | 0 | 100% | No data | No data | No data | No data | 0 | 0 | 100% | No data | No data | No data | No data | 0 | 0 | 100% | 2021-03-01 | 2023-03-10 | No data | No data | 0 | 1238 | 100% | 2021-11-30 | 2024-02-19 | No data | No data | 0 | 243 | 100% | 2021-03-23 | 2023-05-31 | No data | No data | 0 | 541 | 100% | No data | No data | No data | No data | 0 | 0 | 100% | No data | No data | No data | No data | 0 | 0 | 100% | 2021-08-20 | 2021-09-27 | No data | No data | 0 | 3 | 100% | 2021-08-20 | 2021-09-27 | No data | No data | 0 | 0 | 100% | 2021-08-20 | 2021-09-27 | No data | No data | 0 | 0 | 100% | No data | No data | No data | No data | 0 | 0 | 100% | No data | No data | No data | No data | 0 | 0 | 100% | 2021-03-10 | 2023-05-04 | No data | No data | 0 | 430 | 100% | 2021-07-06 | 2022-12-10 | No data | No data | 0 | 430 | 0% | 2021-03-06 | 2021-12-21 | No data | No data | 0 | 430 | 0% | No data | No data | No data | No data | 0 | 0 | 0% | No data | No data | No data | No data | 0 | 0 | 0% | 2021-07-06 | 2023-12-15 | No data | No data | 0 | 4 | 0% | No data | No data | No data | No data | 0 | 1 | 0%
Nirala Trio | 21035 | Balraj Singh | Himanshu Verma | Pallavi Bharadwaj | Active | 5000 | 4572 | 428 | Sebanti(10%), Bipin (10%), Shalini(25%), Shivam(25%) | 56.3% | 704536 | 2021-08-26 | 2021-10-11 | No data | No data | 180 | 161 | 100% | 2021-09-21 | 2021-11-02 | No data | No data | 240 | 47 | 100% | 2024-04-23 | 2025-10-24 | No data | No data | 180 | 461 | 100% | No Data | No Data | No Data | No Data | No Data | No Data | 100% | No Data | No Data | No Data | No Data | No Data | No Data | 100% | 2021-10-05 | 2022-02-18 | No data | No data | 340 | 125 | 100% | 2021-11-12 | 2023-04-13 | No data | No data | 300 | 619 | 100% | 2024-06-17 | 2025-10-17 | 2025-11-07 | No data | 210 | 45 | 100% | No data | No data | No data | No data | No data | No data | 100% | No Data | No Data | No Data | No Data | 250 | 0 | 100% | 2021-10-21 | 2022-10-14 | No data | No data | 250 | 789 | 100% | No data | No data | No data | No data | 160 | 0 | 100% | No data | No data | No data | No data | 140 | 0 | 100% | 2025-08-19 | 2025-10-17 | 2025-11-07 | No data | 100 | 51 | 100% | No data | No data | No data | No data | 0 | 0 | 100% | No data | No data | No data | No data | 135 | 0 | 100% | No data | No data | No data | No data | 45 | 0 | 100% | No data | No data | No data | No data | 60 | 0 | 100% | 2025-08-25 | 2025-10-30 | 2025-11-07 | No data | 60 | 17 | 100% | No data | No data | No data | No data | 0 | 0 | 100% | 2022-03-01 | 2023-06-20 | No data | No data | 165 | 846 | 100% | 2023-06-19 | 2024-05-01 | 2025-02-06 | No data | 275 | 258 | 0% | 2023-07-10 | 2025-10-15 | 2025-11-06 | No Data | 385 | 753 | 0% | No data | No data | No data | No data | 0 | 0 | 0% | 2025-09-08 | 2025-10-30 | 2025-11-07 | No data | 275 | 139 | 0% | 2023-04-17 | 2027-02-28 | No data | No data | 1000 | 49 | 0% | 2027-01-01 | 2027-02-28 | No data | No data | 250 | 184 | 0%
Mirabilis - GH, Ghaziabad | 22013 | Balraj Singh | Ashulika Arora | Pallavi Bharadwaj | Active | 17904 | 685 | 17219 | Bipin (10%), Dheeraj (40%), Kriti (100%) | 63.2% | 1891493 | 2022-05-06 | 2024-11-12 | No data | No data | 537 | 8 | 100% | 2022-05-30 | 2024-05-11 | No data | No data | 644 | 0 | 100% | 2023-08-07 | 2025-10-15 | 2025-10-15 | No data | 537 | 0 | 100% | 2022-07-19 | 2025-07-31 | No Data | No Data | 430 | 0 | 100% | No Data | No Data | No Data | No Data | No Data | No Data | 100% | 2022-09-19 | 2025-09-13 | No data | No data | 1074 | 0 | 100% | 2022-07-11 | 2024-12-11 | No data | No data | 770 | 0 | 100% | 2022-10-13 | 2025-11-15 | 2025-11-15 | No data | 609 | 0 | 100% | 2022-09-09 | 2025-05-28 | No data | No data | 609 | 0 | 100% | 2023-07-17 | 2023-12-05 | No Data | No Data | 895 | 0 | 100% | 2022-06-06 | 2024-11-05 | No data | No data | 895 | 0 | 100% | 2023-12-01 | 2025-05-02 | No data | No data | 1074 | 0 | 100% | 2024-01-24 | 2025-10-28 | No data | No data | 770 | 62 | 100% | 2025-10-15 | 2025-12-15 | No data | No data | 609 | 0 | 100% | 2025-10-01 | 2025-12-30 | No data | No data | 609 | 64 | 100% | 2024-11-18 | 2025-06-17 | No data | 6 | 376 | 0 | 100% | No data | No data | No data | No data | 125 | 0 | 100% | 2023-04-12 | 2025-12-31 | No data | No data | 251 | 0 | 100% | 2025-12-01 | 2025-12-30 | No data | No data | 251 | 0 | 100% | 2026-01-01 | 2026-01-31 | No data | No data | 251 | 0 | 100% | 2023-08-22 | 2025-10-30 | 2025-11-17 | 21 | 394 | 467 | 100% | 2025-03-17 | 2025-12-31 | No data | 76 | 788 | 35 | 4% | 2024-12-04 | 2026-03-31 | No Data | 94 | 1181 | 5 | 4% | 2026-03-01 | 2026-05-31 | No data | No data | 770 | 2 | 0% | 2026-01-01 | 2026-02-28 | No data | No data | 770 | 0 | 0% | 2022-12-22 | 2029-06-01 | No data | No data | 1790 | 17 | 0% | 2029-05-01 | 2029-06-01 | No data | No data | 895 | 0 | 0%
Ace Verde | 22022.1 | Balraj Singh | Not in scope | Not in scope | Active | 17498 | 5679 | 11819 | Bipin (10%), Subodh (100%),Chandan Gupta (100%) | 58.9% | 1879276 | 2024-10-21 | 2025-06-19 | No data | No data | 525 | 473 | 100% | 2024-11-05 | 2025-10-17 | No data | No data | 630 | 38 | 100% | No data | No data | No data | No data | 525 | 0 | 100% | No data | No data | No data | No data | 420 | 0 | 100% | No data | No data | No data | No data | No data | No data | 100% | 2024-10-16 | 2025-10-31 | No data | No data | 1050 | 789 | 100% | 2024-11-12 | 2024-11-19 | No data | No data | 752 | 3 | 100% | No data | No data | No data | No data | 595 | 4 | 100% | No data | No data | No data | No data | 595 | 0 | 100% | 2024-12-02 | 2025-07-21 | No Data | No Data | 875 | 193 | 100% | 2024-11-04 | 2025-04-10 | No data | No data | 875 | 546 | 100% | 2025-02-11 | 2025-12-30 | No data | 15 | 1050 | 1413 | 100% | 2025-04-14 | 2025-12-30 | No data | No data | 752 | 359 | 100% | No data | No data | No data | No data | 595 | 0 | 100% | No data | No data | No data | No data | 595 | 0 | 100% | No data | No data | No data | 2 | 368 | 0 | 100% | No data | No data | No data | No data | 122 | 0 | 100% | No data | No data | No data | No data | 245 | 0 | 100% | No data | No data | No data | No data | 245 | 0 | 100% | No data | No data | No data | No data | 245 | 0 | 100% | 2025-03-07 | 2025-12-31 | No data | 20 | 385 | 911 | 100% | 2025-03-10 | 2026-03-31 | No data | 22 | 770 | 532 | 27.27% | 2026-02-01 | 2026-04-30 | No Data | 161 | 1155 | 162 | 1.83% | 2026-01-01 | 2026-06-30 | No data | No data | 752 | 0 | 0% | No data | No data | No data | No data | 752 | 0 | 0% | 2025-08-01 | 2029-08-31 | No data | No data | 1750 | 62 | 0% | 2029-08-01 | 2029-08-31 | No data | No data | 875 | 152 | 0%
Ace Acre Ville - Master Planning (100 Acre) | 22022.2 | Balraj Singh | Not in scope | Not in scope | Active | 6000 | 2523 | 3477 | Bipin (10%) | 62.2% | No data | 2022-06-22 | 2025-09-10 | No data | No data | 300 | 970 | 100% | 2023-06-02 | 2025-07-04 | No data | No data | 360 | 339 | 100% | No data | No data | No data | No data | 0 | 0 | 100% | No data | No data | No data | No data | 0 | 0 | 100% | No data | No data | No data | No data | No data | No data | 100% | 2024-10-24 | 2025-10-07 | No data | No data | 576 | 32 | 100% | No data | No data | No data | No data | 384 | 4 | 100% | No data | No data | No data | No data | 0 | 0 | 100% | No data | No data | No data | No data | 0 | 0 | 100% | 2024-09-10 | 2024-09-13 | No Data | No Data | 300 | 15 | 100% | 2023-06-05 | 2024-09-27 | No data | No data | 300 | 339 | 100% | 2025-05-05 | 2025-07-03 | No data | No data | 576 | 55 | 100% | No data | No data | No data | No data | 384 | 0 | 100% | No data | No data | No data | No data | 0 | 0 | 100% | No data | No data | No data | No data | 0 | 0 | 100% | No data | No data | No data | No data | 216 | 0 | 100% | No data | No data | No data | No data | 36 | 0 | 100% | No data | No data | No data | No data | 108 | 0 | 100% | No data | No data | No data | No data | 0 | 0 | 100% | No data | No data | No data | No data | 0 | 0 | 100% | 2025-01-08 | 2026-04-30 | No data | No data | 192 | 210 | 100% | 2025-02-18 | 2025-09-26 | 2026-04-30 | No data | 444 | 170 | 0% | 2025-04-14 | 2025-10-27 | 2026-04-30 | No Data | 624 | 270 | 0% | No data | No data | No data | No data | 0 | 0 | 0% | No data | No data | No data | No data | 0 | 0 | 0% | 2025-06-06 | 2026-06-30 | No data | No data | 900 | 50 | 0% | 2026-05-31 | 2026-06-30 | No data | No data | 300 | 69 | 0%
Ace Terra - GH (11 Acres) | 22027 | Balraj Singh | Not in scope | Not in scope | Active | 15299 | 6315 | 8984 | Bipin (10%), Shankey (60%) | 55.2% | 2999658 | 2022-07-12 | 2024-06-04 | No data | No data | 459 | 670 | 100% | 2023-07-06 | 2024-05-02 | No data | No data | 551 | 343 | 100% | No data | No data | No data | No data | 459 | 0 | 100% | No data | No data | No data | No data | 367 | 0 | 100% | No data | No data | No data | No data | No data | No data | 100% | 2023-08-07 | 2025-06-19 | No data | No data | 918 | 853 | 100% | 2023-09-21 | 2025-10-10 | No data | No data | 643 | 25 | 100% | No data | No data | No data | No data | 520 | 0 | 100% | No data | No data | No data | No data | 520 | 0 | 100% | No data | No data | No data | No data | 765 | 0 | 100% | 2023-07-17 | 2024-05-03 | No data | No data | 306 | 1054 | 100% | 2023-12-05 | 2025-01-07 | No data | No data | 536 | 417 | 100% | 2024-02-06 | 2025-11-07 | No data | No data | 382 | 307 | 100% | No data | No data | No data | No data | 306 | 0 | 100% | No data | No data | No data | No data | 306 | 0 | 100% | No data | No data | No data | No data | 321 | 0 | 100% | No data | No data | No data | No data | 107 | 0 | 100% | No data | No data | No data | No data | 214 | 0 | 100% | No data | No data | No data | No data | 214 | 0 | 100% | No data | No data | No data | No data | 214 | 0 | 100% | 2024-01-15 | 2025-07-04 | No data | No data | 337 | 494 | 100% | 2024-09-16 | 2025-12-31 | No data | No data | 673 | 741 | 0% | 2024-09-18 | 2026-03-31 | No data | No data | 1010 | 1170 | 0% | 2026-02-01 | 2026-04-30 | No data | No data | 673 | 0 | 0% | No data | No data | No data | No data | 673 | 0 | 0% | 2024-07-03 | 2028-04-30 | No data | No data | 3060 | 241 | 0% | 2028-08-01 | 2028-08-31 | No data | No data | 765 | 0 | 0%
Ace Estate (68 Acres) - Master Planning, Yamuna Expressway, Greater NOIDA Sec-22D | 22057.1 | Balraj Singh | Not in scope | Not in scope | Active | 6900 | 6556 | 344 | Bipin (10%) | 62.2% | No data | 2022-12-21 | 2025-09-10 | No data | No data | 300 | 1003 | 100% | 2022-12-20 | 2025-10-08 | No data | No data | 360 | 34 | 100% | No data | No data | No data | No data | 0 | 0 | 100% | No data | No data | No data | No data | 0 | 0 | 100% | No data | No data | No data | No data | 0 | 0 | 100% | 2024-05-02 | 2025-09-29 | No data | No data | 576 | 382 | 100% | No data | No data | No data | No data | 384 | 0 | 100% | No data | No data | No data | No data | 0 | 0 | 100% | No data | No data | No data | No data | 0 | 0 | 100% | No data | No data | No data | No data | 300 | 0 | 100% | No data | No data | No data | No data | 300 | 338 | 100% | No data | No data | No data | No data | 576 | 0 | 100% | No data | No data | No data | No data | 384 | 0 | 100% | No data | No data | No data | No data | 0 | 0 | 100% | No data | No data | No data | No data | 0 | 0 | 100% | No data | No data | No data | No data | 216 | 5 | 100% | No data | No data | No data | No data | 36 | 0 | 100% | No data | No data | No data | No data | 108 | 0 | 100% | No data | No data | No data | No data | 0 | 0 | 100% | No data | No data | No data | No data | 0 | 0 | 100% | 2024-07-17 | 2025-07-29 | No data | No data | 192 | 462 | 100% | 2025-01-20 | 2025-05-29 | No data | No data | 444 | 243 | 0% | 2025-05-19 | 2025-09-01 | No data | No data | 624 | 309 | 0% | No data | No data | No data | No data | 0 | 0 | 0% | No data | No data | No data | No data | 0 | 0 | 0% | 2024-12-16 | 2026-01-01 | No data | No data | 900 | 27 | 0% | 2025-12-01 | 2026-01-01 | No data | No data | 300 | 3 | 0%
Elite X - GH, Greater NOIDA | 23064 | Balraj Singh | Surabhi Garg | Pallavi Bharadwaj | Active | 14701 | 16500 | -1799 | Sahil Gupta (50%) | 69.8% | 1570564 | 2023-02-06 | 2024-02-02 | No data | No data | 441 | 1641 | 100% | 2023-04-03 | 2025-09-02 | No data | No data | 529 | 183 | 100% | 2023-07-07 | 2025-10-10 | No data | No data | 441 | 1984 | 100% | 2023-06-26 | 2025-03-13 | No data | No data | 353 | 171 | 100% | No data | No data | No data | No data | 0 | 0 | 100% | 2023-04-13 | 2025-05-01 | No data | No data | 882 | 1575 | 100% | 2023-05-08 | 2025-04-23 | No data | No data | 632 | 345 | 100% | 2024-02-27 | 2025-08-20 | No data | No data | 500 | 207 | 100% | 2024-01-24 | 2025-05-28 | No data | No data | 500 | 300 | 100% | 2023-09-12 | 2025-09-23 | No data | No data | 735 | 348 | 100% | 2023-05-17 | 2023-12-23 | No data | No data | 735 | 1012 | 100% | 2023-12-04 | 2025-05-20 | No data | No data | 882 | 729 | 100% | 2024-04-08 | 2025-05-16 | No data | No data | 632 | 658 | 100% | 2025-03-26 | 2025-10-30 | 2025-09-12 | No data | 2001-05-14 | 2000-11-13 | 100% | 2024-08-06 | 2025-07-16 | No data | No data | 500 | 375 | 100% | 2023-07-06 | 2023-07-06 | No data | No data | 309 | 1 | 100% | No data | No data | No data | No data | 103 | 7 | 100% | No data | No data | No data | No data | 206 | 496 | 100% | 2025-06-05 | 2025-09-23 | No data | No data | 206 | 0 | 100% | No data | No data | No data | No data | 206 | 0 | 100% | 2023-07-28 | 2025-09-05 | No data | No data | 323 | 759 | 100% | 2024-08-08 | 2025-09-10 | No data | No data | 647 | 539 | 0% | 2024-09-17 | 2025-10-06 | No data | No data | 970 | 869 | 0% | 2024-02-24 | 2025-10-01 | No data | No data | 632 | 1258 | 0% | 2025-01-13 | 2025-11-30 | No data | No data | 632 | 1710 | 0% | 2024-07-05 | 2028-09-28 | No data | No data | 1470 | 985 | 0% | 2028-11-01 | 2028-11-30 | No data | No data | 735 | 2 | 0%
Northwind Sanctuary - GH | 24092 | Balraj Singh | TBD | Pallavi Bharadwaj | Active | 14096 | 8216 | 5880 | Deeraj chand (60%) | 65.4% | 507706 | 2024-04-17 | 2025-10-28 | No data | No data | No data | No data | 100% | 2024-09-12 | 2024-09-12 | No data | No data | No data | No data | 100% | 2024-08-05 | 2025-09-30 | 2025-11-30 | No data | No data | No data | 100% | 2024-06-17 | 2025-06-18 | No data | No data | No data | No data | 100% | No data | No data | No data | No data | No data | No data | 100% | 2024-06-03 | 2025-09-11 | No data | No data | No data | No data | 100% | 2024-06-21 | 2024-06-21 | No data | No data | No data | No data | 100% | 2024-06-12 | 2025-09-30 | 2025-11-30 | No data | No data | No data | 100% | 2025-04-14 | 2025-10-06 | No data | No data | No data | No data | 100% | 2024-12-14 | 2025-07-25 | No data | No data | No data | No data | 100% | 2024-10-28 | 2025-01-30 | No data | No data | No data | No data | 100% | 2025-01-27 | 2025-04-15 | No data | No data | No data | No data | 100% | No data | No data | No data | No data | No data | No data | 100% | 2025-10-01 | 2025-10-30 | 2025-12-15 | No data | No data | No data | 100% | 2024-10-04 | 2026-01-30 | No data | No data | No data | No data | 100% | 2025-05-05 | 2025-05-19 | No data | No data | No data | No data | 100% | No data | No data | No data | No data | No data | No data | 100% | No data | No data | No data | No data | No data | No data | 100% | 2025-10-10 | 2025-10-16 | 2025-10-30 | No data | No data | No data | 100% | 2026-02-01 | 2026-02-28 | No data | No data | No data | No data | 100% | 2025-05-16 | 2025-10-30 | No data | No data | No data | No data | 100% | 2025-05-16 | 2025-10-30 | No data | No data | No data | No data | 0% | 2025-08-18 | 2025-11-10 | No data | No data | No data | No data | 0% | 2026-02-15 | 2026-05-30 | No data | No data | No data | No data | 0% | 2025-10-15 | 2025-11-30 | No data | No data | No data | No data | 0% | 2025-03-25 | 2028-08-31 | No data | No data | No data | No data | 0% | 2028-07-30 | 2028-08-30 | No data | No data | No data | No data | 0%
Ace Hanei 6.5 Acres - GH, Greater NOIDA Sec-12 | 24095 | Balraj Singh | Surabhi Garg | Pallavi Bharadwaj | Active | 11904 | 4556 | 7348 | Bipin (20%) | 65.4% | 1565624 | 2023-10-03 | 2024-07-19 | No data | No data | No data | No data | 100% | 2024-06-11 | 2024-06-11 | No data | No data | No data | No data | 100% | 2024-05-21 | 2024-06-11 | No data | No data | No data | No data | 100% | 2024-04-26 | 2024-07-22 | No data | No data | No data | No data | 100% | No data | No data | No data | No data | No data | No data | 100% | 2024-05-13 | 2024-10-08 | No data | No data | No data | No data | 100% | 2024-05-08 | 2025-01-22 | No data | No data | No data | No data | 100% | 2024-05-30 | 2024-07-11 | No data | No data | No data | No data | 100% | No data | No data | No data | No data | No data | No data | 100% | 2024-05-29 | 2024-11-12 | No data | No data | No data | No data | 100% | 2024-05-24 | 2024-07-26 | No data | No data | No data | No data | 100% | 2024-05-14 | 2024-12-03 | No data | No data | No data | No data | 100% | 2025-05-27 | 2025-06-06 | No data | No data | No data | No data | 100% | 2024-06-20 | 2024-07-25 | No data | No data | No data | No data | 100% | 2024-08-05 | 2024-08-05 | No data | No data | No data | No data | 100% | 2024-06-25 | 2025-03-10 | No data | No data | No data | No data | 100% | No data | No data | No data | No data | No data | No data | 100% | No data | No data | No data | No data | No data | No data | 100% | No data | No data | No data | No data | No data | No data | 100% | No data | No data | No data | No data | No data | No data | 100% | 2024-04-29 | 2025-06-25 | No data | No data | No data | No data | 100% | 2025-01-23 | 2025-10-13 | No data | No data | No data | No data | 0% | 2024-10-07 | 2026-04-30 | No data | No data | No data | No data | 0% | 2024-07-22 | 2026-04-30 | No data | No data | No data | No data | 0% | No data | No data | No data | No data | No data | No data | 0% | 2025-08-06 | 2029-09-30 | No data | No data | No data | No data | 0% | 2029-08-30 | 2029-09-30 | No data | No data | No data | No data | 0%
Adani Veris, Gurugram | 24099 | Balraj Singh | Not in scope | Not in scope | Active | 3446 | 13921 | -10475 | Rahul (80%), Pankaj (100%) | 63.2% | 383252 | 2023-09-27 | 2025-01-21 | No data | No data | No data | No data | 100% | 2024-07-08 | 2025-03-27 | No data | No data | No data | No data | 100% | 2024-10-07 | 2024-11-04 | No data | No data | No data | No data | 100% | 2024-10-24 | 2024-10-24 | No data | No data | No data | No data | 100% | No data | No data | No data | No data | No data | No data | 100% | 2024-08-08 | 2025-04-24 | No data | No data | No data | No data | 100% | 2024-08-02 | 2025-01-31 | No data | No data | No data | No data | 100% | 2024-08-13 | 2025-01-17 | No data | No data | No data | No data | 100% | 2024-10-17 | 2025-01-22 | No data | No data | No data | No data | 100% | 2025-02-18 | 2025-02-25 | No data | No data | No data | No data | 100% | 2024-09-25 | 2025-06-13 | No data | No data | No data | No data | 100% | 2025-01-06 | 2025-09-17 | No data | No data | No data | No data | 100% | 2025-02-17 | 2025-09-17 | No data | No data | No data | No data | 100% | 2025-01-27 | 2025-03-21 | No data | No data | No data | No data | 100% | 2025-08-19 | 2025-08-30 | No data | No data | No data | No data | 100% | 2024-09-18 | 2025-11-10 | No data | No data | No data | No data | 100% | 2025-05-19 | 2025-10-07 | No data | No data | No data | No data | 100% | 2025-09-29 | 2025-11-28 | No data | No data | No data | No data | 100% | 2025-03-17 | 2025-11-28 | No data | No data | No data | No data | 100% | 2025-08-05 | 2025-11-28 | No data | No data | No data | No data | 100% | 2025-08-26 | 2025-09-15 | 2025-12-10 | No data | No data | No data | 100% | 2025-09-05 | 2025-09-30 | 2025-12-31 | No data | No data | No data | 0% | 2025-09-30 | 2025-10-31 | No data | No data | No data | No data | 0% | 2025-10-31 | 2025-11-30 | No data | No data | No data | No data | 0% | 2025-08-31 | 2025-09-30 | No data | No data | No data | No data | 0% | 2025-09-08 | 2028-08-31 | No data | No data | No data | No data | 0% | 2028-06-30 | 2028-08-31 | No data | No data | No data | No data | 0%
Atulyam The Bliss, Mohali | 22046 | Not in scope | Himanshu Verma | Not in scope | Active | 5904 | 9485 | -3581 | No INT Deply | 90% | No data | 2025-04-21 | 2025-04-26 | No data | No data | 177 | No data | 100% | 2025-02-17 | 2025-02-21 | No data | No data | 212 | 9 | 100% | 2022-11-10 | 2025-08-12 | No data | No data | 177 | 2943 | 100% | 2023-08-16 | 2024-02-16 | No data | No data | 142 | 57 | 100% | No data | No data | No data | No data | No data | No data | No data | No Data | No Data | No Data | No Data | 354 | 0 | No Data | No Data | No Data | No Data | No Data | 254 | 0 | No Data | 2022-10-20 | 2025-07-18 | No data | No data | 201 | 145 | 100% | No data | No data | No data | No data | 201 | 1199 | No data | No data | No data | No data | No data | 295 | 0 | No data | No data | No data | No data | No data | 295 | 0 | No data | No data | No data | No data | No data | 354 | 0 | No data | No data | No data | No data | No data | 254 | 0 | No data | 2023-01-06 | 2025-07-29 | No data | No data | 201 | 1309 | 100% | No data | No data | No data | No data | 201 | 0 | No data | No data | No data | No data | No data | 124 | 0 | No data | 2025-06-23 | 2025-06-27 | No data | No data | 41 | 19 | No data | No data | No data | No data | No data | 83 | 695 | No data | 2023-02-13 | 2025-07-25 | No data | No data | 83 | 0 | No data | No data | No data | No data | No data | 83 | 0 | No data | No data | No data | No data | No data | 130 | 0 | No data | No data | No data | No data | No data | 260 | 0 | No data | 2023-08-28 | 2023-08-31 | No data | No data | 389 | 17 | No data | 2023-06-12 | 2023-07-18 | No data | No data | 254 | 2020 | No data | 2023-01-27 | 2025-10-31 | No data | No data | 590 | 746 | 100% | 2023-02-07 | 2025-12-31 | No data | No data | 590 | 746 | 0% | No data | No data | No data | No data | 295 | 0 | 0%
Aurika Hotel, Ayodhya | 24093 | Saurabh Joshi | Himanshu Verma | Pallavi Bharadwaj | Active | 6502 | 7495 | -993 | Himanshu(20%), Suyesh(70%), Rajan, Rahul | 0% | 150000 | 2024-05-17 | 2025-09-09 | No data | No data | 195 | 1239 | 0% | 2024-08-14 | 2024-12-06 | No data | No data | 234 | 12 | 0% | 2024-12-04 | 2025-10-15 | 2026-03-16 | No data | 195 | 448 | 0% | 2024-11-27 | 2025-08-27 | No data | No data | 156 | 393 | 0% | No data | No data | No data | No data | No data | No data | No data | 2024-06-05 | 2025-10-29 | No data | No data | 390 | 622 | 0% | 2025-09-01 | 2025-09-15 | No data | No data | 280 | 7 | 0% | 2025-09-01 | 2025-10-31 | 2026-01-23 | No data | 221 | 33 | 0% | 2025-01-30 | 2025-07-04 | No data | No data | 221 | 105 | 0% | 2025-03-20 | 2025-07-03 | No data | No data | 325 | 99 | 0% | 2024-12-17 | 2024-12-18 | No data | No data | 325 | 15 | 0% | 2025-01-06 | 2025-08-31 | 2025-11-03 | No data | 390 | 2440 | 0% | 2025-03-04 | 2025-10-31 | No data | No data | 280 | 1023 | 0% | 2025-09-15 | 2025-11-15 | 2026-03-13 | No data | 221 | 19 | 0% | 2025-05-19 | 2025-11-30 | No data | No data | 221 | 386 | 0% | 2025-05-28 | 2025-09-30 | No data | No data | 136 | 66 | 0% | 2025-09-01 | 2025-09-30 | No data | No data | 46 | 0 | 0% | 2025-09-01 | 2025-09-30 | No data | No data | 91 | 0 | 0% | 2025-11-01 | 2025-11-30 | 2026-03-20 | No data | 91 | 0 | 0% | 2025-12-01 | 2025-12-30 | No data | No data | 91 | 0 | 0% | 2025-09-01 | 2025-09-30 | No data | No data | 143 | 323 | 0% | 2025-09-15 | 2025-10-15 | No data | No data | 286 | 265 | 0% | 2025-10-15 | 2025-11-30 | No data | No data | 429 | 0 | 0% | 2026-01-01 | 2026-03-30 | No data | No data | 280 | 0 | 0% | 2025-12-01 | 2026-01-31 | 2026-05-22 | No data | 280 | 0 | 0% | 2025-09-15 | 2027-09-15 | No data | No data | 650 | 0 | 0% | 2027-08-15 | 2027-09-15 | No data | No data | 325 | 0 | 0%
Fairfox Wave City - GH, Ghaziabad | 24117 | Dakshit Bajaj | Himanshu Verma | Pallavi Bharadwaj | Active | 12402 | 155 | 12247 | No INT Deply | 0% | 650000 | 2024-12-16 | 2025-10-28 | No data | No data | 372 | 18 | 0% | 2025-02-11 | 2025-10-29 | No data | No data | 446 | 137 | 0% | No data | No data | No data | No data | 372 | 0 | 0% | 2025-02-11 | 2025-10-29 | 2025-12-30 | No data | 298 | 0 | 0% | No data | No data | No data | No data | No data | No data | No data | 2025-09-15 | 2025-10-31 | 2025-11-15 | No data | 744 | 0 | 0% | 2025-09-15 | 2025-10-31 | 2025-11-15 | No data | 533 | 0 | 0% | No data | No data | No data | No data | 422 | 0 | 0% | 2025-10-16 | 2025-11-30 | No data | No data | 422 | 0 | 0% | 2025-10-15 | 2025-12-15 | No data | No data | 620 | 0 | 0% | 2025-11-01 | 2025-12-31 | No data | No data | 620 | 0 | 0% | 2026-01-01 | 2026-02-28 | No data | No data | 744 | 0 | 0% | 2026-01-01 | 2026-02-28 | No data | No data | 533 | 0 | 0% | No data | No data | No data | No data | 422 | 0 | 0% | 2026-01-01 | 2026-02-28 | No data | No data | 422 | 0 | 0% | 2026-03-01 | 2026-03-31 | No data | No data | 260 | 0 | 0% | 2026-03-01 | 2026-03-31 | No data | No data | 87 | 0 | 0% | 2026-03-01 | 2026-03-31 | No data | No data | 174 | 0 | 0% | No data | No data | No data | No data | 174 | 0 | 0% | 2026-03-01 | 2026-03-31 | No data | No data | 174 | 0 | 0% | 2026-01-01 | 2026-02-28 | No data | No data | 273 | 0 | 0% | 2026-03-01 | 2026-04-15 | No data | No data | 546 | 0 | 0% | 2026-04-16 | 2026-10-15 | No data | No data | 818 | 0 | 0% | No data | No data | No data | No data | 533 | 0 | 0% | No data | No data | No data | No data | 533 | 0 | 0% | 2026-01-15 | 2030-01-15 | No data | No data | 1240 | 0 | 0% | 2029-12-15 | 2030-01-15 | No data | No data | 620 | 0 | 0%
Indo Group - GH, Guwahati (Phase-1) | 24104 | Ankit Bansal | Himanshu Verma | Pallavi Bharadwaj | Active | 7799 | 2618 | 5181 | Himanshu(5%), Deepanshu(10%), | 0% | 505908 | 2024-10-01 | 2025-02-28 | No data | No data | 273 | 51 | 0% | 2024-11-25 | 2025-08-28 | No data | No data | 187 | 216 | 0% | 2025-03-24 | 2025-10-10 | 2025-11-15 | No data | 187 | 216 | 50% | 2025-01-15 | 2025-07-23 | No data | No data | 187 | 2 | 0% | No data | No data | No data | No data | No data | No data | No data | 2025-03-04 | 2025-08-30 | No data | No data | 468 | 8 | 0% | 2025-03-05 | 2025-08-29 | No data | No data | 355 | 0 | 0% | 2025-08-28 | 2025-11-15 | No data | No data | 265 | 0 | 0% | 2025-07-04 | 2025-09-04 | No data | No data | 265 | 14 | 0% | 2025-07-01 | 2025-10-30 | 2025-11-30 | No data | 390 | 36 | 0% | 2025-02-10 | 2025-10-30 | No data | No data | 156 | 0 | 0% | 2025-08-30 | 2025-09-30 | 2025-10-30 | No data | 273 | 39 | 0% | 2025-09-01 | 2025-09-30 | 2025-10-30 | No data | 195 | 12 | 0% | 2025-09-08 | 2025-12-15 | No data | No data | 156 | 2 | 0% | 2025-09-28 | 2025-12-15 | No data | No data | 156 | 287 | 0% | 2025-06-10 | 2025-11-15 | 2025-11-30 | No data | 164 | 1952 | 0% | 2025-10-01 | 2025-11-15 | 2025-11-30 | No data | 87 | 0 | 0% | 2025-10-01 | 2025-11-15 | 2025-11-30 | No data | 109 | 34 | 0% | 2025-10-01 | 2025-11-15 | No data | No data | 109 | 42 | 0% | 2025-10-01 | 2025-11-15 | 2025-11-30 | No data | 109 | 0 | 0% | 2025-10-06 | 2025-11-30 | No data | No data | 172 | 797 | 0% | 2025-12-01 | 2025-12-31 | No data | No data | 343 | 3 | 0% | 2026-01-01 | 2026-02-28 | No data | No data | 515 | 0 | 0% | 2026-01-01 | 2026-02-28 | No data | No data | 343 | 0 | 0% | 2026-03-01 | 2026-04-30 | No data | No data | 343 | 0 | 0% | 2025-10-01 | 2028-09-30 | No data | No data | 1560 | 0 | 0% | 2028-09-01 | 2028-09-30 | No data | No data | 390 | 0 | 0%
Eelevate Infra - Villa Interior, Goa | 25122 | Not in scope | Himanshu Verma | Pallavi Bharadwaj | Active | 1700 | 7 | 1693 | No INT Deply | 0% | No data | No data | No data | No data | No data | No data | No data | No data | No data | No data | No data | No data | No data | No data | No data | 2025-02-24 | 2025-10-01 | No data | No data | 153 | 0 | 100% | No Data | No Data | No Data | No Data | No Data | No Data | No Data | No Data | No Data | No Data | No Data | 34 | 0 | No data | No data | No data | No data | No data | No data | No data | No data | No data | No data | No data | No data | No data | No data | No data | 2025-04-28 | 2025-10-13 | No data | No data | 272 | 7 | 0% | No data | No data | No data | No data | No data | No data | No data | 2025-04-28 | 2025-08-08 | No data | No data | 85 | 0 | 0% | No data | No data | No data | No data | No data | No data | No data | No data | No data | No data | No data | No data | No data | No data | No data | No data | No data | No data | No data | No data | No data | No data | No data | No data | No data | 272 | 0 | 0% | No data | No data | No data | No data | No data | No data | No data | No data | No data | No data | No data | No data | No data | No data | No data | No data | No data | No data | No data | No data | No data | No data | No data | No data | No data | No data | No data | No data | No data | No data | No data | No data | 102 | 0 | 0% | No data | No data | No data | No data | No data | No data | No data | No data | No data | No data | No data | No data | No data | No data | No data | No data | No data | No data | No data | No data | No data | No data | No data | No data | No data | No data | No data | No data | No data | No data | No data | No data | No data | No data | No data | No data | No data | No data | No data | 442 | 0 | 0% | No data | No data | No data | No data | 442 | 0 | 0% | No data | No data | No data | No data | 340 | 0 | 0%
Golf Estate(Jashn Realty) - Marketing Office, Lucknow | 25134 | Himanshu Verma | Himanshu Verma | Not in scope | Active | 2000 | 405 | 1595 | Himanshu(5%), Apporva(100%), Vrinda(25%) | 14% | 11840 | 2025-05-19 | 2025-07-31 | No data | No data | 72 | 0 | 100% | No data | No data | No data | No data | No data | No data | 100% | 2025-07-15 | 2025-08-29 | No data | 1 | 60 | 0 | 100% | No Data | No Data | No Data | No Data | No Data | No Data | No Data | 2025-08-29 | 2025-10-24 | No Data | No Data | 12 | 0 | 100% | 2025-07-28 | 2025-09-12 | 2025-11-25 | 19 | 136 | 9 | 100% | 2025-09-02 | 2025-10-14 | No data | No data | 120 | 28 | 100% | 2025-09-02 | 2025-10-14 | 2025-11-25 | 6 | 84 | 60 | 100% | No data | No data | No data | No data | No data | No data | No data | No data | No data | No data | No data | 200 | 0 | No data | No data | No data | No data | No data | No data | No data | No data | 2025-09-03 | 2025-10-27 | 2026-01-05 | 28 | 64 | 44 | 0% | 2025-09-16 | 2025-10-28 | No data | No data | 56 | 46 | 0% | 2025-10-15 | 2025-11-15 | 2026-01-13 | 38 | 40 | 218 | 0% | No data | No data | No data | No data | No data | No data | No data | 2025-10-15 | 2025-10-30 | 2026-01-23 | No data | 54 | 0 | 0% | 2025-10-15 | 2025-10-30 | 2026-01-23 | No data | 18 | 0 | 0% | 2025-10-15 | 2025-10-30 | 2026-01-23 | No data | 24 | 0 | 0% | 2025-10-15 | 2025-10-30 | 2026-01-23 | No data | 24 | 0 | 0% | No data | No data | No data | No data | No data | No data | No data | 2025-11-01 | 2025-11-15 | 2026-01-07 | 4 | 66 | 0 | 0% | 2025-11-16 | 2025-11-30 | 2026-01-27 | 1 | 110 | 0 | 0% | 2025-12-01 | 2026-01-30 | No data | No data | 154 | 0 | 0% | No data | No data | No data | No data | No data | No data | No data | 2025-11-01 | 2025-11-30 | 2026-03-11 | 35 | 110 | 0 | 0% | No data | No data | No data | No data | 400 | 0 | 0% | No data | No data | No data | No data | 100 | 0 | 0%
Trevana (Karyan) - Club & SA, Ghaziabad | 26167 | Palin Sikari | Himanshu Verma | Not in scope | Active | 5000 | 182 | 4818 | Himanshu(20%), Vrinda(50%), Sonali(10%) | 0% | No data | No data | No data | No data | No data | No data | No data | No data | No data | No data | No data | No data | No data | No data | No data | No data | No data | No data | No data | 450 | 182 | 0% | No Data | No Data | No Data | No Data | No Data | No Data | No Data | No Data | No Data | No Data | No Data | 100 | 0 | 0% | No data | No data | No data | No data | No data | No data | No data | No data | No data | No data | No data | No data | No data | No data | No data | No data | No data | No data | 800 | 0 | 0% | No data | No data | No data | No data | No data | No data | No data | No data | No data | No data | No data | 259 | 0 | No data | No data | No data | No data | No data | No data | No data | No data | No data | No data | No data | No data | No data | No data | No data | No data | No data | No data | No data | No data | No data | No data | No data | No data | No data | No data | 800 | 0 | 0% | No data | No data | No data | No data | No data | No data | No data | No data | No data | No data | No data | No data | No data | No data | No data | No data | No data | No data | No data | No data | No data | No data | No data | No data | No data | No data | No data | No data | No data | No data | No data | No data | 300 | 0 | 0% | No data | No data | No data | No data | No data | No data | No data | No data | No data | No data | No data | No data | No data | No data | No data | No data | No data | No data | No data | No data | No data | No data | No data | No data | No data | No data | No data | No data | No data | No data | No data | No data | No data | No data | No data | No data | No data | No data | No data | 1300 | 0 | 0% | No data | No data | No data | No data | 1000 | 0 | 0% | No data | No data | No data | No data | No data | No data | 0%
Smart World One DXP, Gurugram | 26168 | Not in scope | Himanshu Verma | Not in scope | Active | 0 | 194 | -194 | Himanshu(20%)Suyesh(25%), Deepanshu(90%), Agrima(50%) | 0% | No data | No data | No data | No data | No data | No data | No data | No data | No data | No data | No data | No data | No data | No data | No data | No data | No data | No data | No data | 0 | 0 | 100% | No Data | No Data | No Data | No Data | No Data | No Data | No Data | No Data | No Data | No Data | No Data | 0 | 0 | 0% | No data | No data | No data | No data | No data | No data | No data | No data | No data | No data | No data | No data | No data | No data | No data | No data | No data | No data | 0 | 0 | 100% | No data | No data | No data | No data | No data | No data | No data | No data | No data | No data | No data | 0 | 0 | 0% | No data | No data | No data | No data | No data | No data | No data | No data | No data | No data | No data | No data | No data | No data | No data | No data | No data | No data | No data | No data | No data | No data | No data | No data | No data | 0 | 0 | 100% | No data | No data | No data | No data | No data | No data | No data | No data | No data | No data | No data | No data | No data | No data | No data | No data | No data | No data | No data | No data | No data | No data | No data | No data | No data | No data | No data | No data | No data | No data | No data | No data | 0 | 13 | 30% | No data | No data | No data | No data | No data | No data | No data | No data | No data | No data | No data | No data | No data | No data | No data | No data | No data | No data | No data | No data | No data | No data | No data | No data | No data | No data | No data | No data | No data | No data | No data | No data | No data | No data | No data | No data | No data | No data | No data | 0 | 181 | 30% | No data | No data | No data | No data | 0 | 0 | 0% | No data | No data | No data | No data | No data | No data | 0%
Gaur City Mall, Greater Noida | 25140 | Not in scope | Himanshu Verma | Pallavi Bharadwaj | Active | 4545 | 51 | 4494 | No INT Deply | 39% | 75681 | 2023-06-23 | 2025-08-20 | No data | No data | 164 | 0 | 0% | 2025-06-02 | 2025-10-07 | No data | No data | 218 | 0 | 0% | 2025-06-02 | 2025-10-07 | No data | No data | 136 | 0 | 100% | 2025-09-01 | 2025-09-30 | 2025-11-30 | No Data | 0 | 0 | 0% | 2025-08-27 | 2025-10-31 | No Data | No Data | 27 | 2 | 0% | 2025-06-19 | 2025-09-30 | No data | No data | 309 | 14 | 0% | No data | No data | No data | No data | 273 | 0 | No data | 2025-07-11 | 2025-10-30 | No data | No data | 191 | 7 | 100% | 2025-10-01 | 2025-10-30 | 2025-12-30 | No data | 0 | 0 | 0% | 2025-10-15 | 2025-11-30 | No data | No data | 227 | 0 | 0% | No data | No data | No data | No data | 227 | 0 | 0% | 2025-11-01 | 2025-11-30 | No data | No data | 145 | 0 | 0% | No data | No data | No data | No data | 127 | 0 | 0% | 2025-11-01 | 2025-11-30 | No data | No data | 91 | 9 | 100% | 2025-11-01 | 2025-11-30 | 2026-01-30 | No data | 0 | 0 | 0% | 2025-11-01 | 2025-11-15 | No data | No data | 123 | 5 | 0% | No data | No data | No data | No data | 41 | 0 | 0% | 2025-11-01 | 2025-11-15 | No data | No data | 55 | 0 | No data | 2025-11-01 | 2025-11-30 | No data | No data | 55 | 0 | 100% | 2025-11-01 | 2025-11-30 | No data | No data | 0 | 0 | 0% | No data | No data | No data | No data | 150 | 0 | 0% | No data | No data | No data | No data | 250 | 0 | 0% | 2025-12-01 | 2025-12-30 | No data | No data | 350 | 0 | 0% | 2025-12-01 | 2025-12-30 | No data | No data | 0 | 0 | 0% | 2025-12-01 | 2025-12-30 | No data | No data | 250 | 0 | 0% | 2026-01-01 | 2026-07-30 | No data | No data | 909 | 6 | 0% | No data | No data | No data | No data | 227 | 0 | 0%
Solus Uptown Mall, Raipur | 18004 | Subrata Seth | Ashulika Arora | Pallavi Bharadwaj | Active | 6000 | 8968 | -2968 | Subrata (5%),Avnish(100%), Rahul(20%), Soni(5%) | 69.8% | 578766 | 2022-02-04 | 2025-11-03 | No data | 0 | 210 | 0 | 100% | 2025-08-01 | 2025-10-20 | No Data | 0 | 144 | 0 | 100% | 2022-07-07 | 2025-10-16 | No Data | 0 | 144 | 0 | 100% | 2025-09-10 | 2025-09-30 | No Data | 0 | 144 | 17 | 100% | No Data | No Data | No Data | No Data | No Data | No Data | 100% | 2021-09-16 | 2024-05-17 | No data | 32 | 360 | 0 | 100% | 2023-07-14 | 2025-10-31 | 2025-10-30 | 11 | 258 | 0 | 100% | 2025-10-01 | 2025-10-30 | No Data | 91 | 204 | 0 | Sudipto | 2025-11-15 | 2025-12-15 | No Data | 0 | 204 | 41 | No Data | 2025-10-15 | 2025-11-15 | No data | 0 | 300 | 0 | 100% | 2025-09-15 | 2025-10-15 | No Data | 0 | 120 | 0 | 100% | 2025-10-01 | 2025-10-31 | 2026-01-15 | 34 | 210 | 0 | 100% | 2025-10-15 | 2025-10-31 | No Data | 11 | 150 | 0 | 100% | 2025-11-15 | 2025-12-31 | No Data | 91 | 120 | 34 | No Data | 2026-01-01 | 2026-02-28 | No Data | 0 | 120 | 64 | No Data | 2025-09-15 | 2025-09-29 | No Data | 42 | 126 | 0 | 100% | 2025-08-22 | 2025-09-30 | 2025-11-30 | No Data | No Data | No Data | 100% | 2025-11-01 | 2025-11-15 | 2025-11-30 | 5 | 84 | 0 | No Data | 2025-12-01 | 2025-12-31 | No Data | 91 | 84 | 0 | No Data | 2026-03-01 | 2026-03-30 | No Data | 0 | 84 | 0 | No Data | 2023-07-06 | 2023-07-26 | No Data | 4 | 132 | 35 | 100% | 2025-08-01 | 2025-10-15 | No Data | 20 | 264 | 140 | 100% | 2025-10-16 | 2025-11-30 | 2026-02-27 | 33 | 396 | 492 | 0% | 2026-04-01 | 2026-06-30 | No Data | 0 | 264 | 0 | No Data | 2025-11-01 | 2025-12-31 | No Data | 91 | 264 | 202 | No Data | 2022-01-04 | 2027-04-30 | No Data | 0 | 1200 | 39 | 0% | 2025-04-01 | 2027-04-30 | No Data | 0 | 300 | 0 | 0%
Ace Medley Mall, Sec 150 Noida | 18006 | Subrata Seth | TBD | TBD | Active | 8500 | 1792 | 6708 | Soni(5%) | 95% | 211363 | No Data | No Data | No Data | No Data | 168 | 0 | 100% | No Data | No Data | No Data | No Data | 224 | 0 | 100% | No Data | No Data | No Data | No Data | 168 | 99 | 100% | No Data | No Data | No Data | No Data | No Data | No Data | No Data | No Data | No Data | No Data | No Data | 0 | 0 | 100% | No Data | No Data | No Data | No Data | 318 | 0 | 100% | No Data | No Data | No Data | No Data | 280 | 0 | 100% | No Data | No Data | No Data | No Data | 196 | 82 | 100% | No Data | No Data | No Data | No Data | No Data | No Data | No Data | No Data | No Data | No Data | No Data | 234 | 0 | 100% | No Data | No Data | No Data | No Data | 234 | 0 | 100% | No Data | No Data | No Data | No Data | 150 | 0 | 100% | No Data | No Data | No Data | No Data | 131 | 0 | 100% | No Data | No Data | No Data | No Data | 94 | 1 | No Data | No Data | No Data | No Data | No Data | No Data | No Data | No Data | No Data | No Data | No Data | No Data | 126 | 0 | 100% | No Data | No Data | No Data | No Data | 42 | 0 | 100% | No Data | No Data | No Data | No Data | 56 | 0 | No Data | No Data | No Data | No Data | No Data | 56 | 0 | No Data | No Data | No Data | No Data | No Data | No Data | No Data | No Data | No Data | No Data | No Data | No Data | 154 | 149 | 100% | No Data | No Data | No Data | No Data | 257 | 288 | 100% | No Data | No Data | No Data | No Data | 360 | 301 | 100% | No Data | No Data | No Data | No Data | No Data | No Data | No Data | No Data | No Data | No Data | No Data | 257 | 401 | No Data | No Data | No Data | No Data | No Data | 935 | 354 | 0% | No Data | No Data | No Data | No Data | 234 | 115 | 0%
Skya Realtech - MLU, Faridabad | 25150 | Eshaan Goyal | Himanshu Verma | Pallavi Bharadwaj | Active | 501 | 255 | 246 | No INT Deply | 0% | 1533148 | 2025-09-29 | 2025-10-10 | No data | No data | 15 | 255 | 0% | No data | No data | No data | No data | 18 | 0 | No data | No data | No data | No data | No data | 12 | 0 | 0% | No data | No data | No data | No data | 12 | 0 | No data | No data | No data | No data | No data | 3 | 0 | No data | No data | No data | No data | No data | 30 | 0 | No data | No data | No data | No data | No data | 22 | 0 | No data | No data | No data | No data | No data | 17 | 0 | 0% | No data | No data | No data | No data | 17 | 0 | No data | No data | No data | No data | No data | 25 | 0 | No data | No data | No data | No data | No data | 10 | 0 | No data | No data | No data | No data | No data | 18 | 0 | No data | No data | No data | No data | No data | 12 | 0 | No data | No data | No data | No data | No data | 10 | 0 | 0% | No data | No data | No data | No data | 10 | 0 | No data | No data | No data | No data | No data | 10 | 0 | No data | No data | No data | No data | No data | 4 | 0 | No data | No data | No data | No data | No data | 7 | 0 | No data | No data | No data | No data | No data | 7 | 0 | 0% | No data | No data | No data | No data | 7 | 0 | No data | No data | No data | No data | No data | 11 | 0 | No data | No data | No data | No data | No data | 22 | 0 | No data | No data | No data | No data | No data | 33 | 0 | No data | No data | No data | No data | No data | 22 | 0 | No data | No data | No data | No data | No data | 22 | 0 | No data | No data | No data | No data | No data | 100 | 0 | 0% | No data | No data | No data | No data | 25 | 0 | 0%
Apex Quebec - GH, Ghaziabad | 20006 | Subrata Seth | Not in scope | Not in scope | Active | 14900 | 15054 | -154 | Subrata (5%), Ruchir(10%) | 59.6% | 1533148 | 2021-05-03 | 2024-09-02 | No Data | No Data | 447 | 94 | 100% | 2022-02-23 | 2023-06-12 | No Data | No Data | 536 | 185 | 100% | 2022-05-04 | 2025-02-21 | No Data | No Data | 447 | 214 | 100% | No Data | No Data | No Data | No Data | 358 | 0 | No Data | No Data | No Data | No Data | No Data | No Data | No Data | 100% | 2021-05-12 | 2022-06-21 | No Data | No Data | 894 | 228 | 100% | 2021-06-28 | 2021-10-01 | No Data | No Data | 626 | 436 | 100% | 2021-05-17 | 2022-07-22 | No Data | No Data | 507 | 327 | 100% | 2021-08-04 | 2023-05-10 | No Data | No Data | 507 | 240 | No Data | 2022-02-28 | 2022-09-01 | No Data | No Data | 745 | 476 | 100% | 2021-05-04 | 2024-08-01 | No Data | No Data | 298 | 1455 | 100% | 2021-05-05 | 2023-12-01 | No Data | No Data | 522 | 2040 | 100% | 2022-02-15 | 2024-05-15 | No Data | No Data | 372 | 1639 | 100% | 2022-07-04 | 2023-11-23 | No Data | No Data | 298 | 400 | No Data | 2022-03-11 | 2023-12-01 | No Data | No Data | 298 | 228 | No Data | 2021-05-04 | 2024-04-09 | No Data | No Data | 313 | 174 | 100% | 2024-04-09 | 2024-04-09 | No Data | No Data | 104 | 2 | 100% | 2021-09-29 | 2021-10-21 | No Data | No Data | 209 | 0 | No Data | No Data | No Data | No Data | No Data | 209 | 66 | No Data | 2021-10-01 | 2021-11-22 | No Data | No Data | 209 | 26 | No Data | 2022-05-10 | 2023-08-02 | No Data | No Data | 328 | 370 | 100% | 2022-10-11 | 2024-01-22 | No Data | No Data | 656 | 637 | 100% | 2022-05-13 | 2024-10-11 | No Data | No Data | 983 | 1820 | 100% | 2023-09-07 | 2025-09-03 | No Data | No Data | 656 | 627 | No Data | 2023-06-20 | 2023-11-29 | No Data | No Data | 656 | 428 | No Data | 2022-08-16 | 2026-12-31 | No Data | No Data | 2980 | 2884 | 0% | 2026-12-01 | 2026-12-31 | No Data | No Data | 745 | 37 | 0%
Ace Acre Ville (100 Acres) - Club & Commercial, Greater Noida Sec-22A | 22022.4 | Subrata Seth | Not in scope | Not in scope | Active | 9900 | 7049 | 2851 | Subrata (5%), Soni(25%), Pawan(100%),Shruti(100%),Piyush(100%),Rahul(15%) | 22% | 40343 | 2024-09-02 | 2025-03-19 | 2024-10-28 | 1 | 495 | 433 | 100% | 2024-09-06 | 2025-10-31 | No Data | 1 | 594 | 653 | 100% | No Data | No Data | No Data | No Data | No Data | No Data | 100% | No Data | No Data | No Data | No Data | No Data | No Data | No Data | No Data | No Data | No Data | No Data | No Data | No Data | 100% | 2024-09-16 | 2025-11-03 | No Data | 39 | 950 | 930 | 100% | 2025-01-09 | 2025-10-17 | No Data | 4 | 634 | 929 | 100% | No Data | No Data | No Data | No Data | No Data | No Data | 50% | No Data | No Data | No Data | No Data | No Data | No Data | No Data | 2025-09-19 | 2025-10-15 | No Data | 1 | 495 | 229 | 100% | 2024-12-02 | 2025-09-17 | No Data | 1 | 495 | 925 | 100% | 2024-12-02 | 2025-11-14 | 2025-12-26 | 56 | 0 | 0 | 100% | 2024-12-17 | 2025-12-05 | 2025-12-26 | 6 | 0 | 0 | 100% | No Data | No Data | No Data | No Data | No Data | No Data | No Data | No Data | No Data | No Data | No Data | No Data | No Data | No Data | 2025-10-15 | 2025-12-31 | 2026-02-13 | 36 | 256 | 10 | 100% | 2025-10-15 | 2025-12-31 | 2026-02-13 | No Data | 59 | 0 | 100% | 2026-01-08 | No Data | 2026-02-13 | 11 | 0 | 0 | No Data | No Data | No Data | No Data | No Data | No Data | No Data | No Data | No Data | No Data | No Data | No Data | No Data | No Data | No Data | 2025-09-01 | 2025-11-07 | 2026-01-30 | 6 | 317 | 300 | 0% | 2025-10-01 | 2025-12-12 | 2026-02-27 | 32 | 733 | 93 | 0% | 2025-11-01 | 2026-02-28 | 2026-06-30 | 104 | 1030 | 233 | 0% | No Data | No Data | No Data | No Data | No Data | No Data | No Data | No Data | No Data | No Data | No Data | No Data | No Data | No Data | 2025-12-01 | 2028-06-30 | No Data | 00-Jan-00 | 2004-01-24 | 2000-01-28 | 0% | 2028-06-01 | 2028-06-30 | No Data | 0 | 495 | 0 | 0%
Ace Estate (68 Acres)- Club & Commercial, Yamuna Express Way, Greater Noida Sec-22D | 22057.2 | Subrata Seth | Not in scope | Not in scope | Active | 6900 | 6263 | 637 | Subrata(10%), Vivek(100%), Manjit (100%), Soni (15%),Rahul(15%) | 59% | 36031 | 2024-09-24 | 2025-02-20 | No Data | 1 | 345 | 94 | 100% | 2025-01-13 | 2025-09-18 | No Data | 1 | 414 | 195 | 100% | No Data | No Data | No Data | No Data | No Data | No Data | 100% | No Data | No Data | No Data | No Data | No Data | No Data | No Data | No Data | No Data | No Data | No Data | No Data | No Data | 100% | 2024-09-09 | 2025-10-31 | No Data | 58 | 662 | 211 | 100% | 2024-09-10 | 2025-10-31 | No Data | 4 | 442 | 1159 | 100% | No Data | No Data | No Data | No Data | No Data | No Data | 50% | No Data | No Data | No Data | No Data | No Data | No Data | No Data | 2025-06-23 | 2025-10-31 | No Data | 1 | 345 | 247 | 100% | 2024-09-05 | 2025-03-20 | No Data | 1 | 345 | 567 | 100% | 2024-09-11 | 2025-11-12 | 2025-12-20 | 76 | 662 | 941 | 100% | 2024-10-07 | 2025-11-12 | 2025-12-20 | 7 | 442 | 936 | 100% | No Data | No Data | No Data | No Data | No Data | No Data | No Data | No Data | No Data | No Data | No Data | No Data | No Data | No Data | 2025-10-15 | 2025-11-30 | 2025-12-31 | 74 | 248 | 1061 | 100% | 2025-10-15 | 2025-11-30 | 2025-12-30 | 0 | 41 | 21 | 100% | 2025-10-15 | 2026-11-30 | 2026-01-01 | 19 | 124 | 0 | No Data | No Data | No Data | No Data | No Data | No Data | No Data | No Data | No Data | No Data | No Data | No Data | No Data | No Data | No Data | 2024-09-01 | 2025-11-04 | 2026-01-30 | 5 | 221 | 587 | 0% | 2025-10-01 | 2025-12-31 | 2026-02-06 | 26 | 511 | 316 | 0% | 2025-11-01 | 2026-02-28 | No Data | 134 | 718 | 201 | 0% | No Data | No Data | No Data | No Data | No Data | No Data | No Data | No Data | No Data | No Data | No Data | No Data | No Data | No Data | 2025-12-01 | 2028-06-30 | No Data | No Data | 1035 | 18 | 0% | 2028-06-01 | 2028-06-30 | No Data | 0 | 245 | 0 | 0%
Titanium SPR (Signature Global) - GH, Gurugram Sec-71 (Phase-1) | 23083 | Subrata Seth | Surabhi Garg | Not in scope | Active | 18200 | 16827 | 1373 | Subrata(10%), Mohak(100%),Rahul janda(100%),Varun(25%) | 55% | 3059990 | 2024-01-22 | 2025-09-15 | No Data | 1 | 655 | 0 | 100% | 2024-02-27 | 2025-09-12 | No Data | 1 | 874 | 0 | 100% | 2025-07-01 | 2026-09-03 | No Data | No Data | 655 | 0 | 0% | No Data | No Data | No Data | No Data | No Data | No Data | No Data | No Data | No Data | No Data | No Data | No Data | No Data | 100% | 2024-01-15 | 2025-01-02 | No Data | 1 | 1238 | 0 | 100% | 2024-01-18 | 2025-08-29 | No Data | 1 | 1092 | 0 | 100% | 2025-08-22 | 2025-10-31 | No Data | 0 | 764 | 0 | Surabhi | No Data | No Data | No Data | No Data | No Data | No Data | No Data | 2024-04-15 | 2024-09-19 | No Data | 1 | 910 | 0 | 100% | 2024-01-18 | 2025-03-06 | No Data | 1 | 910 | 0 | 100% | 2024-01-15 | 2025-11-06 | No Data | 244 | 582 | 198 | 100% | 2024-06-18 | 2025-11-06 | No Data | 140 | 510 | 238 | 100% | 2025-08-22 | 2025-09-21 | No Data | 0 | 364 | 23 | No Data | No Data | No Data | No Data | No Data | No Data | No Data | No Data | 2024-05-14 | 2025-08-08 | No Data | 1 | 491 | 0 | 100% | 2024-05-14 | 2025-08-08 | No Data | 1 | 164 | 0 | 100% | 2025-05-14 | 2025-08-08 | No Data | 0 | 218 | 0 | No Data | 2025-01-21 | 2025-02-14 | No Data | No Data | 218 | 0 | No Data | No Data | No Data | No Data | No Data | No Data | No Data | No Data | 2025-06-01 | 2025-10-15 | No Data | 38 | 601 | 0 | 100% | 2025-06-01 | 2025-09-30 | 2026-02-23 | 169 | 1001 | 858 | 100% | 2024-05-16 | 2025-10-31 | 2026-02-23 | 357 | 1401 | 531 | 100% | No Data | No Data | No Data | No Data | No Data | No Data | No Data | 2025-01-20 | 2025-09-30 | No Data | 0 | 1001 | 0 | No Data | 2025-06-03 | 2028-12-31 | No Data | 0 | 3640 | 176 | 0% | 2028-12-01 | 2028-12-31 | No Data | 0 | 910 | 0 | 0%
SSR Greater Noida | 26164 | TBD | Himanshu Verma | Pallavi Bharadwaj | Active | 30502 | 419 | 30083 | No INT Deply | 0% | 24,34,786 | No data | No data | No data | No data | 915 | 246 | No data | No data | No data | No data | No data | 1098 | 173 | No data | No data | No data | No data | No data | 732 | 0 | 0% | No data | No data | No data | No data | 732 | 0 | No data | No data | No data | No data | No data | 183 | 0 | No data | No data | No data | No data | No data | 1830 | 0 | No data | No data | No data | No data | No data | 1312 | 0 | No data | No data | No data | No data | No data | 1037 | 0 | 0% | No data | No data | No data | No data | 1037 | 0 | No data | No data | No data | No data | No data | 1525 | 0 | No data | No data | No data | No data | No data | 1525 | 0 | No data | No data | No data | No data | No data | 1830 | 0 | No data | No data | No data | No data | No data | 1312 | 0 | No data | No data | No data | No data | No data | 1037 | 0 | 0% | No data | No data | No data | No data | 1037 | 0 | No data | No data | No data | No data | No data | 640 | 0 | No data | No data | No data | No data | No data | 214 | 0 | No data | No data | No data | No data | No data | 427 | 0 | No data | No data | No data | No data | No data | 427 | 0 | 0% | No data | No data | No data | No data | 427 | 0 | No data | No data | No data | No data | No data | 671 | 0 | No data | No data | No data | No data | No data | 1342 | 0 | No data | No data | No data | No data | No data | 2013 | 0 | No data | No data | No data | No data | No data | 1312 | 0 | No data | No data | No data | No data | No data | 1312 | 0 | No data | No data | No data | No data | No data | 3050 | 0 | 0% | No data | No data | No data | No data | 1525 | 0 | 0%
Cloverdale SPR (Signature Global) - GH, Gurugram Sec-71 (Phase-2) | 24110 | Subrata Seth | Surabhi Garg | Not in scope | Active | 14200 | 6620 | 7580 | Subrata(25%),Soni (50%)Aliza(100%), Shalini(100%), Rohit(100%) | 42% | 2640061 | 2024-12-15 | 2025-01-31 | No Data | 0 | 511 | 14 | 100% | 2025-01-01 | 2025-01-31 | No Data | 0 | 682 | 93 | 100% | 2025-10-01 | 2025-11-07 | No Data | 0 | 511 | 362 | 0% | No Data | No Data | No Data | No Data | No Data | No Data | No Data | No Data | No Data | No Data | No Data | No Data | No Data | 100% | 2025-07-22 | 2025-11-14 | No Data | 123 | 966 | 534 | 100% | 2025-07-22 | 2025-11-14 | No Data | 10 | 852 | 199 | 100% | 2025-11-07 | 2025-12-06 | No Data | 0 | 611 | 294 | Surabhi | No Data | No Data | No Data | No Data | No Data | No Data | No Data | 2025-04-01 | 2025-10-10 | No Data | 0 | 710 | 390 | 100% | 2025-02-17 | 2025-06-30 | No Data | 0 | 710 | 1292 | 100% | 2025-08-22 | 2026-01-16 | No Data | 167 | 454 | 1737 | 100% | 2025-10-01 | 2026-01-30 | 2026-03-30 | 0 | 398 | 1158 | 50% | 2025-11-07 | 2025-12-06 | No Data | 0 | 284 | 260 | No Data | No Data | No Data | No Data | No Data | No Data | No Data | No Data | 2025-10-15 | 2026-02-13 | No Data | 0 | 383 | 52 | 100% | 2025-10-15 | 2026-02-13 | No Data | 0 | 114 | 4 | 0% | 2025-10-15 | 2026-02-13 | No Data | 0 | 170 | 0 | No Data | 2025-12-07 | 2025-12-21 | No Data | 0 | 170 | 0 | No Data | No Data | No Data | No Data | No Data | No Data | No Data | No Data | 2025-10-01 | 2026-03-06 | No Data | 20 | 469 | 281 | 100% | 2025-10-16 | 2026-03-20 | 2026-05-29 | 0 | 781 | 213 | 0% | 2026-01-01 | 2026-05-30 | No Data | 234 | 1093 | 370 | 0% | No Data | No Data | No Data | No Data | No Data | No Data | No Data | 2025-12-22 | 2026-01-31 | No Data | 0 | 781 | 0 | No Data | 2025-10-01 | 2029-09-30 | No Data | 0 | 2840 | 14 | 0% | 2029-05-01 | 2029-06-01 | No Data | 0 | 710 | 0 | 0%
Apex Serene Residency - GH, Greater Noida | 25141 | Subrata Seth | Surabhi Garg | Not in scope | Active | 13500 | 1615 | 11885 | Subrata(40%), Varun(75%), Arvind(100%), Danish(100%), Rahul(50%) | 3.6% | 24,34,786 | 2025-06-24 | 2025-09-12 | No Data | No Data | 486 | 1442 | 0% | 2025-09-12 | 2025-10-10 | 2026-01-15 | No Data | 648 | 355 | 0% | No Data | No Data | No Data | No Data | 405 | 3 | 0% | No Data | No Data | No Data | No Data | No Data | No Data | 0% | 2025-10-15 | 2025-10-31 | 2026-01-15 | No Data | 81 | 26 | 0% | 2025-11-01 | 2025-12-15 | No Data | No Data | 918 | 59 | 0% | 2025-12-16 | 2026-01-31 | No Data | No Data | 810 | 0 | 0% | 2025-12-16 | 2026-01-31 | No Data | No Data | 567 | 0 | Surabhi | No Data | No Data | No Data | No Data | No Data | No Data | No Data | 2026-01-16 | 2026-02-28 | No Data | No Data | 675 | 1 | 0% | 2025-12-15 | 2026-01-16 | No Data | No Data | 675 | 0 | 0% | 2025-12-15 | 2026-01-16 | No Data | No Data | 432 | 0 | 0% | 2025-12-15 | 2026-01-15 | No Data | No Data | 378 | 34 | 0% | 2025-12-15 | 2026-01-15 | No Data | No Data | 270 | 0 | No Data | No Data | No Data | No Data | No Data | No Data | No Data | No Data | 2025-12-15 | 2026-01-15 | No Data | No Data | 364 | 0 | 0% | 2026-01-15 | 2026-02-15 | No Data | No Data | 122 | 0 | 0% | 2026-02-16 | 2026-02-28 | No Data | No Data | 162 | 0 | No Data | No Data | No Data | No Data | No Data | 162 | 0 | No Data | No Data | No Data | No Data | No Data | No Data | No Data | No Data | 2026-02-16 | 2026-02-28 | No Data | No Data | 446 | 0 | 0% | 2026-03-01 | 2026-04-30 | No Data | No Data | 742 | 0 | 0% | 2026-04-01 | 2026-06-30 | No Data | No Data | 1040 | 2 | 0% | No Data | No Data | No Data | No Data | No Data | No Data | No Data | No Data | No Data | No Data | No Data | 742 | 0 | No Data | 2026-02-01 | 2030-02-01 | No Data | No Data | 2700 | 7 | 0% | 2029-12-01 | 2030-02-01 | No Data | No Data | 675 | 0 | 0%
give